## R13.1.0 Issues Backlog
Id | Component | Module | Title | Priority | Status | Date Opened | Description | CMS Impact | Release Date
81529 | Patient Safety | Analysis and Reporting | Blank reports are displayed when Filters are applied on Modify screen | 2-High | New | 2023-04-13 | Blank reports are displayed when Filters are applied on Modify screen. This issue must be fixed across all 6 reports. 1)Rate Table - Hospital-onset Antimicrobial Resistance Incidence 2)Rate Table - Hospital-onset Positive Culture Incidence by Organism 3)Rate Table - Community-onset Antimicrobial Resistance Prevalence 4)Rate Table - Community-onset Positive Culture Prevalence by Organism 5)Rate Table - Outpatient Antimicrobial Resistance Prevalence 6)Rate Table - Outpatient Positive Culture Prevalence by Organism | No | TBD
81536 | Healthcare Personnel Safety | COVID-19 | Supergroup Blank Report and Export Blank | 2-High | New | 2023-09-28 | Supergroup cannot run reports/export data sets under the Healthcare Personnel Safety Component for COVID 19 - Vaccination Facility, Line Listing - All COVID19 Cumulative Summary Data-Facility. Notification of "No Records found" is received and the exported file has no data. | No | TBD
81543 | Patient Safety | Analysis and Reporting | All HAIs A&R Reports for Group Users Dropping Data >5 Years Prior | 1-Urgent | New | 2024-03-14 | Data from 2015 and forward should be included in the 2015 Baseline SIR reports. 2016-2017 data is not included in the report. | Yes | TBD
81547 | Patient Safety | Antimicrobial Use Resistance | DSG is failing when there is a "format PATHOGEN not found error" for PS component | 1-Urgent | New | 2024-06-29 11:49 | The DSGs are erroring out for some facilities and groups in the PS component due to a format PATHOGEN error. The error message is: The format PATHOGEN was not found or could not be loaded. | Yes | TBD
81554 | Neonatal | Analysis and Reporting | NEO patients - Missing Variables in ADS | 3-Medium | New | 2021-10-29 | There were variables discovered as missing in the analysis data set (ADS). | No | TBD
81555 | Neonatal | Analysis and Reporting | Issues with Create ADS and Reports for NEO_ParticipationAlert | 3-Medium | New | 2022-02-11 | Several variables are missing from the variable drop down. A footnote is missing in regards to users with limited rights. | No | TBD
81557 | Patient Safety | Analysis and Reporting | AUR - Blank reports are displayed when generated for Rate tables when changed Display Options groupby to summary YH | 2-High | New | 2023-04-06 14:16 | Blank reports are displayed when generated for Rate tables when changed Display Options groupby to summary YH. | No | TBD
81558 | Long Term Care | Analysis and Reporting | LTC_ltc_SVH_COVID19_Event.sas program is taking a long time to run in the DSG process for large groups | 3-Medium | New | 2023-04-19 | DSG for large LTCF group should run in under 1 hour or less. DSG took more than one hour. | No | TBD
81560 | Patient Safety | Analysis and Reporting | A&R Plot suppression issues | 1-Urgent | New | 2023-05-15 16:19 | The SAAR reports and SAAR Plot reports should use the same suppression rules. Currently, the data in the SAAR Plot reports are sometimes suppressed when they are not suppressed in the SAAR reports. The SAAR reports should be the source of truth for what should and should not be suppressed. | No | TBD
81561 | Patient Safety | Analysis and Reporting | Correct AUR SAS code for multi-drug resistant AR Option assignments | 2-High | New | 2023-09-06 | The code for assigning the multi-drug phenotypes for Psuedomonas aerginosa and Acinetobacter phenotypes is incorrectly categorizing not tested and resistant isolates for the AR Option. | No | TBD
81580 | Patient Safety | Antimicrobial Use Resistance | AR Option Group Antibiogram groupBy cumulative showing negative values | 2-High | New | 2024-04-08 | When running the AR Option Antibiogram rate table within an NHSN Group and modified by groupBy = cumulative, the second table in the report shows negative values. Negative values should not be possible in this report. | No | TBD
81584 | Long Term Care | Other | Group Resident Find doesn't return any results when selected With Specified Identifiers | 2-High | New | 2024-04-22 | LTC Group Resident - FIND Search is not displaying results when selected with Specified Identifiers. | No | 2025-05-01
81588 | Patient Safety | Analysis and Reporting | MBI CCN is incorrect | 2-High | New | 2024-04-30 | There is an S in the third position of the CCN number for an oncology unit running their MBI-LCBI report | No | TBD
81598 | Patient Safety | Analysis and Reporting | Pediatric TAS Report - Location Groups (Combined) - Issues with other SAAR types tables | 2-High | New | 2023-02-07 | The "TAS Report - Pediatric SAAR Types - Location Groups (Combined)" report appears to be broken. The table(s) that contains data for all the other SAAR types (non-ALL) includes a row for the ALL SAAR type which it should not. In addition, not all the available Location Groups & SAAR types are being included in the table and there are repeating AU-CAD values. All the AU-CAD values and other data (antimicrobial days, days present, etc.) appear to be incorrect when compared to the Location Groups (Separated) report. This happens for all groupBy levels. | No | TBD
81599 | Patient Safety | Antimicrobial Use | Group AR Option Incidence Reports - Cumulative Patient Days Not Displaying for All Facilities | 2-High | New | 2023-04-17 12:44 | When running the Rate Table - Hospital-onset Positive Culture Incidence by Organism report with groupBy=cumulative, the denominator data (patient days) is not displaying for some facilities. | No | TBD
81600 | Patient Safety | Analysis and Reporting | A&R Plot displays incomplete time periods for SummaryYH and SummaryYr | 1-Urgent | New | 2023-05-15 13:03 | Similar to the SAAR reports, the SAAR Plot reports should only display data for completed time periods. Currently, the SAAR Plot reports will display completed time periods for summaryYM and summaryYQ (e.g. not displaying data for 2023M05 or 2023Q2), but will display incomplete time periods for summaryYH and summaryYr (e.g. displaying data for 2023H1 and 2023 in May 2023). | No | TBD
81608 | Patient Safety | Other | Unable to delete Multiple records during Procedure csv import | 3-Medium | New | 2024-06-29 11:57 | User was unable to delete over 18 rows. | No | TBD
81610 | Patient Safety | Other | Unable to delete Multiple records during Surgeon csv import | 3-Medium | New | 2024-06-29 11:57 | User should be able to Delete more than 10 rows at a time. User can only delete 2 rows. | No | TBD
83592 | Patient Safety | Analysis and Reporting | Large group(s) unable to run DSG | 2-High | New | 2024-03-19 | DSG is unsuccessful. | No | TBD
85737 | Patient Safety | Analysis and Reporting | Group AUR PI Status report not reflecting AR summary from outpatient location | 1-Urgent | New | 2024-09-06 10:49 | The Group line list does not take into account AR Summary records submitted for outpatient location types (ED, pediatric ED or 24hr-observation). The facility does not get a "Yes" in the ARSummaryFlag column despite having submitted an AR Summary record for that month. | Yes | TBD
90793 | Patient Safety | Antimicrobial Use Resistance | Intermittent errors when uploading AR Events | 2-High | New | 2025-01-08 11:39 | Despite the file having no errors, it fails to upload the first time. | No | TBD
91151 | Patient Safety | Antimicrobial Use Resistance | Two AR Events with single eventID | 2-High | New | 2025-01-14 14:34 | Each orgID/patientID/specimen group/pathogen should be considered a unique event and should not share an EventID with another event. There should be only one result per AR Drug Test for a given event. | No | TBD
91347 | Patient Safety | Survey | Enrollment survey is adding mandatory partial survey questions (HOSP, LTAC and IRF) | 2-High | New | 2025-01-17 07:35 | When completing the survey during enrollment, more questions are required than should be. Some of these questions should be completed during the partial survey after enrollment, not during enrollment | No | TBD
91761 | Patient Safety | Survey | Number of beds = 0 in partial PS Hosp survey | 2-High | New | 2025-01-24 09:34 | The facility should not have been able to save 0 beds in the production. | No | TBD
92523 | All | Analysis and Reporting | Error retrieving output messages upon running Report without running DSG | 2-High | New | 2025-02-11 14:49 | An error message displays when trying to display the report. | No | TBD
92937 | Outpatient Procedure | Analysis and Reporting | No 'print list' link is available for users to access. | 2-High | New | 2025-02-24 08:25 | The print list link does not display | No | TBD
93672 | Dialysis | Analysis and Reporting | Sex field not populating in patient line listing | 2-High | New | 2025-03-13 | The sex field (column BP) should be populated with M (male), F (Female) or blank if other/unknown had been previously selected. As the user indicated they only used M/F, all rows should be populated. The entire Sex column (column BP) is blank. | No | 2025-06-21
93935 | Outpatient Procedure | Procedures | Recognizing Multiple Procedures for Nov and Dec | 2-High | New | 2025-03-19 | When submitting November and December data for the Outpatient Procedure Component, a message stating displayed that there were duplicate bilateral procedure codes for HER, though the associated CPT code is different. These patients had multiple hernias repaired thus the two CPT codes | No | 2025-06-21